## SLCTR/2014/021

Brief description of research carried out during the reporting period

Following approval of my protocol change (change of one study centre – Please see attached previous communication, annex A, on this matter) by Ethics Review Committee and Research and Higher Degrees Committee of Faculty of Medicine, Colombo, preparations were made for data collection from 30/11/2015. However, due to following reasons first patient was recruited on 13/01/2016:

- Approval from Sri Lanka Clinical Trials Registry for protocol change was obtained by 03/12/2015.

- Two of the study instruments (MMQa and MMQb) needed extensive training by staff in application as they were found to be too complicated during practical application.

- Sluggishness in initiation of getting patients for recruitment until the potential referral parties (other wards, OPD etc) became familiar with the process of sending potential study participants.

Results / Observations.

Relevant staff have been trained on recruitment and carrying out the treatments according to manual of the study protocol. Twelve participants have been recruited so far.

Outcomes

No publications yet. Last progress report submitted via RHDC in May 2016.

Difficulties encountered

- Training of staff took longer as I had to train novice therapists at the new study centre. Their training is still going on, while they have started delivering therapy under my supervision.

- Recruitment of participants has been slower than expected. A campaign has been launched with multiple approaches, such as posters displayed widely, emails etc to spread the invitation to send patients to the Alcohol Clinic so they may be potential study participants.

Explanation of the dealy:

Recruitment of participants and data collection were delayed by three months and the first participant was recruited in January 2016.

- Approval from Sri Lanka Clinical Trials Registry for protocol change was obtained only by 03/12/2015.

- Two of the study instruments (MMQa and MMQb) needed extensive training by staff in application as they were found to be too complicated during practical application.

- Training of staff took longer as I had to train novice therapists at the new study centre. Their training is still going on, while they have started delivering therapy under my supervision.

End or report.

Mahesh Rajasuriya

05/08/2016